


















University of Maryland, Baltimore
Bressler Research Building – Seventh Floor Renovation	Project No: 10-357
95% Construction Document Submission Phase	March 11, 2011
SECTION 013300 – SUBMITTAL PROCEDURES
Latest Update: 8/6/2026
(A/E shall edit specifications and blue text in header to meet project requirements. This includes but is not limited to updating Equipment and/or Material Model Numbers indicated in the specifications and adding any additional specifications that may be required by the project. Remove text underlines and highlights)  
GENERAL
SUMMARY
This Section includes administrative and procedural requirements for submittals by the Contractor as required by the contract documents. 
SUBMITTAL REGISTER
Prepare a Submittal Register in spreadsheet format for use in the PMIS. Register will include the following for each anticipated submittal:
Specification Title
Category
Specification Section
Submit Register for review prior to first application for payment.
SUBMITTAL SCHEDULE
Submittal Schedule: Contractor shall prepare and submit a Submittal Schedule which lists submittal items per the product specifications for review and approval by the Architect.  Contractor shall allow fifteen (15) days for Architect and University review. The Submittal Schedule shall identify all specified submittals to be made and shall serve as a checklist for submittals. Arrange the submittals in numerical order by specification section. Include time required for review, ordering, manufacturing, fabrication, and delivery when establishing dates. Include additional time required for making corrections or revisions to submittals noted by Architect and additional time for handling and reviewing submittals required by those corrections.
1. Use the Preliminary Project Submittal Register as a basis for identifying required submittals, including requirements for concurrent submittals, and complex submittals which may require additional review time by the Architect at Initial Review.
2. Coordinate Submittal Schedule with list of subcontracts, the Schedule of Values, and Contractor's construction schedule.
3. Format: Submit the Submittal Schedule as a Microsoft Excel file or as designated by the UMB PM. Use the University-provided excel template which can be found in the University PMIS submittal folder. 
4. Review of any submittal without submission and approval of submittal schedule does not relieve Contractor of responsibility to provide Submittal Schedule for approval.  
5. Contractor shall revise Submittal Schedule as required to include addition or deletion of submittals during project duration. 
1.2 SUBMITTAL FORMATS
A. Action Submittals: 
Only include information from a single specification section. Submittals may not bundle products or equipment from multiple spec sections. Contractor may use their own discretion on how information is divided and number of submittals provided under each specification section.
Product Data can be submitted before or concurrent with Shop Drawings and with Samples unless otherwise noted in individual specification sections. Product data, shop drawings, color charts and/or samples can be submitted as a single submittal where appropriate.
Each Action Submittal shall clearly indicate the products that will be provided by the contractor, including indicating selected options. Where published data sheets are provided which indicate the availability of multiple products or multiple options/selections for products, clearly mark the submittal using arrows, clouds, boxes, or highlighting to indicate intended options and selections for each product. 
Do not include manufacturer’s warranty and/or operation and maintenance instructions in Action Submittals. Include this information in the project operation and maintenance manual submittal. 
Only include information related to the specific materials used on the project. Do not submit complete product catalogs. Submittals with excess unrelated content will be returned without review.
Informational and Closeout Submittals: 
Submit Informational and Closeout submittals separately from Action Submittals.
Processing Submittals: 
Submittals are processed electronically using University PMIS. Transmit all submittals from Contractor to Architect via University PMIS unless otherwise directed. Submittals received from sources other than the Contractor will be returned without action. Include all submittal identification information specified below.
1.3 SUBMITTAL IDENTIFICATION FORM
Use the standard UMB Submittal Identification Form, as the first page of the submittal file. Fill out the following information for each submittal at a minimum:
Project name and University project number.
Submittal Title and Revision
Submittal name shall match University PMIS Submittal Register.
Specification Section
Include subsection if project uses condensed specifications.
Submission date.
Name of Architect or Primary Consultant.
Name of Contractor.
Names of subcontractor or firm that prepared the submittal as applicable.
Identification of the Contract Document issue date and revision upon which the submittal is based.
Submittals not including a Submittal Identification Form will be returned as “Not Reviewed”.
The Submittal Identification Form shall be updated by each reviewer to show review action, notes, signature, and date. Architect or Prime Designer will note final review action before returning to the contractor.
The Submittal Identification form shall remain the first page of the submittal throughout the review process.
CONTRACTOR SUBMITTAL COVER SHEET
Use the Contractor, subcontractor or vendor cover, as the second page of the submittal file. Contractor should use their standard cover sheet for this page which shall include the following information for each submittal at a minimum:
Project name and University project number.
Submission date.
Name and address of Contractor.
Name of firm or entity that prepared submittal.
Names of subcontractor, manufacturer, and supplier as applicable.
Category: Action or Informational.
Specification section.
Identification of the Contract Document issue date and revision upon which the submittal is based (including addenda, early release packages, or phased design submissions, if applicable).
Unique submittal title, including revision identifier. 
Type of submittal (product data, test report, etc.). 
When a submittal item includes multiple types of submittals (Product Data, Shop Drawings, Qualifications, etc) note all that apply.  
University PMIS only allows selection of one type of submittal. When multiple submittal types are submitted together, choose the category that is the most explanatory. 
All listed information shall be identical to that listed in the approved University PMIS Submittal Register.
Other necessary identification.
Contractor’s certification that information submitted complies with requirements of the Contract Documents, to include, but not be limited to, quantities, dimensions, and coordination with other work.
Identify each element in a Submittal Item by a unique identifier that can be used to clearly correlate the submittal with Contract Drawings such as: 
Specifications article and paragraph ,
Drawing number.
ID number in drawing schedule, 
Assembly or Equipment number, 
Other pertinent identifying information 
Clearly and explicitly identify all deviations from the Contract Documents, including minor variations and limitations. If Contractor fails to identify deviations they certify that the submittal fully complies with the Contract Documents. 
Input each Submittal Item using the University PMIS Submittal Module using identical information from the approved Submittal Schedule. 
Options: When a specific feature such as color has been selected as part of the design, mark the selection on the submittal. If the selection is not in the project design, provide options available for selection by the Architect.
SUBMITTAL PDF FILE REQUIREMENTS
PDF Submittals: Prepare submittals as a single PDF. Incorporate complete information into the PDF file. 
Remove all extraneous material such as installation instructions, operations and maintenance manuals, and product catalogs.
Submitted PDF shall have searchable text throughout. Optical Character Recognition (OCR) is not acceptable.
Bookmarks: Include bookmarks for files larger than 15 pages. Set bookmarks for each product in the submittal file. Label each product bookmark with the Title, Specification Article Number, or Equipment Designation if applicable. See examples below and sample bookmarks in Part 3:
 Example: 
2.2 Shut Off Valves
2.4 Check Valves
2.5 Special Valves 
AHU-1
Clearly identify submitted products and any selected options and selections for each product when multiple options are shown in submitted product data. Mark the selections in the pdf using arrows, clouds, boxes or highlighting.
University Selected Options: When the specification does not identify a manufacturer’s specific feature, such as color, provide options available for selection by the Architect and University.
A submittal must be complete without any external links. Hyperlinks to documents on the web are not allowed and are not acceptable as a substitution for product data. 
Submittal File Names
Submittal file names shall follow the convention: 
[UMB Project Number][UMB specification section number][submittal title].pdf. 
For projects using condensed specifications: 
[UMB Project Number][ UMB division number, article number][submittal title].pdf. 
Avoid long file names. Use names which are identifiable when compared to the University PMIS Submittal Register. Provide revision number where applicable. 
See examples below: 
Full Version Specification: 
19-357 087100 Door Hardware.pdf
19-357 230523 Valves for HVAC Piping Systems.pdf
Condensed Specification: 
19-357 22 - 2.6 Plumbing Valves.pdf 
19-357 23 - 2.2 HVAC Valves R1.pdf
Contractor’s file names shall not be altered by the A/E and UMB except adding the A/E and UMB Initials (XXX) at each review step. See examples below: 
Full Version Specification: 
19-357 087100 Door Hardware AE.pdf
19-357 230523 Valves for HVAC Piping Systems AE UMB.pdf
Condensed Specification: 
19-357 22 - 2.6 Plumbing Valves AE.pdf
19-357 23 - 2.2 HVAC Valves R1 AE UMB.pdf
SUBMITTAL PROCEDURES
[bookmark: _Hlk69721506]Prepare and submit types of submittals with submittal items as required by individual Specification Sections. Examples of types of submittals include product data, shop drawings, color charts and/or samples.  Each submittal shall be one University PMIS item.
Use the University PMIS Submittal Module to create each Submittal Item. Persons entering submittals shall be trained by UMB on the University PMIS Submittal Module prior to entering the Submittal Schedule and any other submittals. Upload the pdf of the submittal directly to the University PMIS Submittal Module. 
Coordination: 
Coordinate schedule for preparation and processing of submittals with performance of construction activities such as fabrication, purchasing, testing, delivery, other submittals, and related activities that require sequential activity.
Submit all submittal items required for each Specification Section concurrently unless partial submittals for portions of the Work are approved by the UMB PM.
Where a work process includes requirements under separate specification sections, submit these submittals at the same time to avoid delays in processing due to requirement for concurrent review. EDIT FOR PROJECT AND CLEARLY PROVIDE INSTRUCTIONS TO CONTRACTOR IN PRELIMINARY SUBMITTAL REGISTER 
Specific submittals need to be reviewed concurrently, including but not limited to, the following:
087100 Door Hardware with 281300 Access Control System
042100 Brick and Mortar. 
090000 Wall and floor finishes for coordination of colors. 
Submittals that require selection of colors will be reviewed. Color selection may not be provided until all submittals requiring color selection have been received and reviewed, and color selections have been approved by the Architect. 
Architect reserves the right to withhold action on a submittal requiring coordination with other submittals until related submittals are received.
Submittal Comments: Submittal comment markups entered on the submittal by the Supplier, CM / Contractor, Consultant (A/E), and UMB Personnel shall use the following colors.
Supplier, CM / Contractor: Dark Green
Consultant (A/E): Red
UMB: Blue
Processing Time: 
Time for review shall commence on Architect's receipt of submittal.  No extension of the Contract Time will be authorized because of failure to transmit submittals enough in advance of the work to permit processing, including resubmittals.
Submittal review, including time for resubmittals is assigned as follows: 
Initial Review: Allow 15 working days for initial review of each submittal (which includes University’s review) 
10 business days for AE review
5 business days for University Review
Complicated submittals may be allocated additional time as noted on the approved Submittal Schedule. Allow additional time if coordination with concurrent submittals is required. The Architect will advise Contractor when a submittal being processed must be delayed for coordination.
Initial Review of Concurrent Submittals: Allow additional time if coordination with concurrent submittals is required. Architect will advise Contractor when a submittal being processed must be delayed for coordination.
Initial Review of Complex Submittals: At the time of review and approval of the Submittal Schedule, the Architect will advise Contractor of certain submittals that are substantially complicated or require multiple reviewers and need an extended initial review time, including but not limited to, the following:
EDIT FOR PROJECT AND PROVIDE INSTRUCTIONS TO CONTRACTOR IN PRELIMINARY SUBMITTAL REGISTER
081113 Hollow Metal Doors and Frames (21 days)
084413 Glazed Aluminum Curtainwall (30 days).
087100 Door Hardware (21 days).
123600 Wood Laboratory Furniture (21 days)
142100 Elevators (45 days) includes Elevator Inspector review.
210000 Fire Protection Submittal (45 days) includes Fire Marshal review.
230923 Control Sequences (21 days)
281300 Access Control System (21 days)
282300 Video Surveillance (21 days)
283111 Digital Addressable Fire-Alarm System (45 days) includes Fire Marshal review.
Resubmittals: Allow 15 days for review of each resubmittal.
Resubmittals: Make resubmittals in same form as initial submittal.
Note date and content of previous submittal only (do not include entire rejected submittal).
Note date and content of revision in Submittal Identification Form. 
Clearly indicate extent of revision on Contractor’s Cover Sheet. 
Provide responses to Architect’s review comments as appropriate to address concerns raised. 
Annotate the product data sheets, shop drawings, calculations, etc. to clearly indicate compliance with the original specification requirements and to demonstrate compliance with review comments.
Do not resubmit partial submittals. Resubmittal must be complete.
Submittals shall be resubmittal until they are marked as Approved by the Architect.
Delegated Design Services Certification: In addition to other required submittals, submit digitally-signed and sealed PDF electronic file of the certificate by the responsible design professional through the University PMIS.
Distribution: Electronic access to final submittals will be provided through the University PMIS to manufacturers, subcontractors, suppliers, fabricators, installers, authorities having jurisdiction, and others as necessary for performance of construction activities. 
Use for Construction: Use University PMIS as the system of record for all submittals used on Project site. Use only final action submittals that are marked with approval notation from Architect's action stamp.
CONTRACTOR’S REVIEW OF SUBMITTALS
Contractor’s Review of Submittals: Collect complete submittal documentation from the Sub/Manufacturer, create the Submittal Package, and assign Submittal Items to it. Each Submittal Item shall be reviewed by the contractor prior to submission to Architect for review,
The contractor and associated subcontractors are responsible for reviewing and verifying the submittal is complete and complies with all the requirements of the construction documents. If the submittal does not comply, the contractor shall identify the deficiencies and promptly return the submittal to the vendor for correction. If the incomplete or incorrect submittal is forwarded on to the A/E and/or UMB, the contractor is responsible for any cost issues resulting from re-processing the submittals.
Include one Submittal Identification Form for each Submittal Item.  The Contractor shall certify that submittals have been reviewed and approved and mark on form. Mark each Submittal Item with a uniform approval stamp including the name of the reviewer and the date of the Contractor’s approval and sign each Submittal Item in the designated location on the form.  Submittals without stamp and signature will not be reviewed and will be returned. Electronic signatures are acceptable. 
Contractor’s submittal approval certifies the following actions have been completed by the Contractor:
Field measurements have been determined and verified.
Conformance with requirements of Contract Drawings and Specification is confirmed.
Catalog numbers and similar data are correct and indicated with arrow or highlighting; items not used, but on same page shall be crossed out.  
Work being performed by various subcontractors and trades is coordinated.
Field construction criteria have been verified, including confirmation that information submitted has been coordinated with the work being performed by others for the University and actual site conditions.
All deviations from requirements of Drawings and Specifications have been identified and noted. 
Submittals not certified by being stamped and signed by Contractor electronically on the Submittal Identification Form will be returned without action, as will submittals which, in the Architect’s opinion, have not been adequately reviewed and coordinated by Contractor.
Changes in Work: Changes in the Work shall not be authorized by submittal review actions.  No review action, implicit or explicit, shall be interpreted to authorize changes in the Work. Changes shall only be authorized by separate written direction from the University, in accordance with the Contract General Conditions. However, to minimize the ordering of incorrect equipment/parts, notes may indicate forthcoming changes via CDC.
Submittal Comments: Submittal comments entered on the submittal by the Supplier, CM / Contractor, shall follow the assigned color codes:
Supplier, CM / Contractor: Dark Green
REVIEW OF SUBMITTALS BY ARCHITECT AND UNIVERSITY
Review of Submittals by Architect and University:  
Reviews by University, Architect and Architect's consultants are for general conformance with the design concept of the Project and general compliance with the information given in the Drawings and Specifications.
The Architect’s review shall not be construed as an “approval,” or to relieve the Contractor(s) and material suppliers of responsibility for errors or omissions in the submitted documents.
Acceptance of a specific item does not include acceptance of the assembly of which the item is a component.
Architect will review each submittal, mark to indicate action taken, and return promptly via the web-based software (University PMIS) system.
Exception: Submittals for record, information or similar purposes 
Architect’s Review Action: Architect will mark each submittal with a uniform, self-explanatory action. Architect’s action may use a stamp on the Submittal Identification Form and may also include a separate review sheet on Architect’s standard form following the Submittal Identification Form. 
When review is made by a subconsultant to determine action taken, architect remains responsible for marking final review action.
<The below listing of submittal actions are the University standard stamp action and the abbreviation/notation for University PMIS.  If A/E’s stamp abbreviation/notations differ provide the equivalent as highlighted below.>
Submittal will be appropriately marked as follows to indicate the action taken:
Action 1 APP (no exceptions taken): Fabrication, manufacture, or construction may proceed providing submittal complies with Contract Documents.
Equivalent to Architect’s stamp Action <Insert Note Here>.
Action 2a AAN (note markings; no resubmission required): Fabrication, manufacture, or construction may proceed providing submittal complies with additional Architect's review notations and Contract Documents.  (Note: If Contractor cannot comply with notations, make revisions and resubmit.)
Equivalent to Architect’s stamp Action <Insert Note Here>.
Action 2b RFR (note markings/resubmit for record): Fabrication, manufacture, or construction may proceed; however, submittal did not fully demonstrate full extent of all conditions, details and coordination with other surrounding work. Update submittal with required additional information and rework as noted and resubmit for record.  Should Contractor proceed with fabrication, manufacturing or construction, it shall do so at its own risk.
Equivalent to Architect’s stamp Action <Insert Note Here>.     
Action 3 A&R (amend and resubmit): This is the equivalent to R&R (revise and resubmit): Submittal does not comply with design intent of Contract Documents.  Do not use submittals stamped Action 3. Make revisions and resubmit.
Equivalent to Architect’s stamp Action <Insert Note Here>.
Action 4 REJ (rejected, submit specified item or resubmit with related assembly items): Submittal varies significantly from specified item or system specified in Contract Documents and is not acceptable for use on the project. Do not use submittals stamped Action 4. Make revisions and resubmit.
Equivalent to Architect’s stamp Action <Insert Note Here>.
Action 6 NAR (no action required):  Documents have not been reviewed by Architect and submittal is returned to Contractor for several possible reasons: submittal not requested, submittal not complete, Submittal Transmittal form is not included, submittal not coordinated, or submittal bears no resemblance to design intent. Architect shall identify which reason is applicable on form.
 Equivalent to Architect’s stamp Action <Insert Note Here>.
Do not permit submittals marked "Rejected, or Revise and Resubmit" to be used at the Project site, or elsewhere where Work is in progress. 
Any work performed prior to receiving a fully approved submittal shall be done at the Contractor's risk and shall be subject to being replaced if Contract requirements are not met.
Submittal Comments: Submittal comments entered on the submittal by Consultant (A/E), shall follow the assigned color codes:
Consultant (A/E): Red
University Review: University Review: The University will note review of the submittal on the Submittal ID sheet and upload the submittal to University PMIS.
Submittal Comments: Submittal comments entered on the submittal by UMB Personnel shall follow the assigned color codes, as follows:
UMB: Blue
Final Review Action: After receiving University Review notes, the Architect will provide final Action for the submittal and return stamped submittal to the Contractor.
Contractor Action: The Contractor will be notified through University PMIS that the submittal is ready for their action. The Contractor shall incorporate all review comments and resubmit if required by the University PMIS and Architect’s actions and markings.
Contract Requirements:
Review actions by Architect and Architect's consultants or the University do not relieve the Contractor from compliance with requirements of the Contract Drawings and Specifications.
Acceptance of submittals with deviations do not relieve Contractor from responsibility for additional costs of changes required to accommodate such deviations.
Deviations included in submittals without prior written acceptance shall not be considered approved, regardless of whether such deviations are identified in review comments or in the returned submittal.
No review action, implicit or explicit, shall be interpreted to authorize changes in the Work.  Changes shall only be authorized by separate written Change Order or Field Instruction, in accordance with the Contract General Conditions. 
When professional certification of performance criteria of materials, systems or equipment is required by Contract Documents, the Architect shall be entitled to rely upon accuracy and completeness of such calculations and certifications.
Resubmittals are subject to same terms and conditions as original submittal.
The University will not accept excessive resubmittals.	
Provide a summary of changes made to revised submittal from the previous submission.
Should excessive resubmittals be required, Contractor may be subject to reimburse the University for Architect's costs for time spent in processing additional resubmittals at their contractual hourly rate. 
SUBMITTAL REQUIREMENTS
Product Data: Collect information into a single submittal for each element of construction and type of product or equipment included in the specification section.
If information must be specially prepared for submittal because standard published data are unsuitable for use, generate specific shop drawings for the submittal, and identify as product data. 
Mark each submittal to show which products and options are applicable. Clearly indicate all aspects of the proposed items, including material selections and all options specified. Failure to indicate such details could result in the submittal being returned as incomplete.
Include the following information, as applicable:
Manufacturer's catalog cuts.
Manufacturer's product specifications.
Standard color charts.
Statement of compliance with specified referenced standards.
Testing by recognized testing agency, including credentials. 
Application of testing agency labels and seals.
Notation of coordination requirements.
Availability and delivery time information.
For equipment, include the following in addition to the above, as applicable:
Wiring diagrams that show factory-installed wiring.
Printed performance curves.
Operational range diagrams.
Clearances required to other construction, if not indicated on accompanying Shop Drawings.
Shop Drawings: Prepare and submit Project-specific information, drawn accurately to scale. Do not base Shop Drawings on reproductions of the Contract Documents or standard printed data, unless submittal based on Architect's digital data drawing files is otherwise permitted.
Preparation: Fully illustrate requirements as shown in the Contract Documents.  Include the following information, as applicable:
Identification of products.
Schedules.
Compliance with specified standards.
Notation of coordination requirements.
Notation of dimensions established by field measurement.
Relationship and attachment to adjoining construction clearly indicated.
Seal and signature of professional engineer if specified.
University PMIS:  Submit each submittal as a single PDF file through the University PMIS, with any scaled drawings capable of being printed as a full-size drawing.
Samples: Submit Samples for review of kind, color, pattern, and texture for a check of these characteristics with other materials.
Transmit Samples that contain multiple, related components such as accessories together in one submittal package.
Sample Identification: Permanently attach label on unexposed side of Samples that includes the following:
Project name and submittal number.
Generic description of Sample.
Product name and name of manufacturer.
Sample source.
Number and title of applicable Specification Section.
Specification paragraph number and generic name of each item.
Transmittal: Provide Submittal Identification Form and include complete submittal information indicated. Include photos of actual sample with sample identification label clearly shown as well as any illustrating sample characteristics and sample identification information for record.
University PMIS: Prepare transmittal in PDF form, and upload to University PMIS. Enter required data in University PMIS to fully identify submittal.
Disposition: Maintain sets of approved Samples at Project site, available for quality-control comparisons throughout the course of construction activity. Sample sets may be used to determine final acceptance of construction associated with each set.
Samples that may be incorporated into the Work are indicated in individual Specification Sections. Such Samples must be in an undamaged condition at time of use.
Samples not incorporated into the Work, or otherwise designated as University’s property, are the property of Contractor.
Samples for Initial Selection: Submit manufacturer's color charts consisting of units or sections of units showing the full range of colors, textures, and patterns available.
Number of Samples: Submit two full sets of available choices where color, pattern, texture, or similar characteristics are required to be selected from manufacturer's product line. Architect will return one set with options selected.
Samples for Verification: Submit full-size units or Samples of size indicated, prepared from same material to be used for the Work, cured and finished in manner specified, and physically identical with material or product proposed for use, and that show full range of color and texture variations expected. 
Samples include, but are not limited to, the following: 
partial sections of manufactured or fabricated components; 
small cuts or containers of materials; 
complete units of repetitively used materials; 
swatches showing color, texture, and pattern; 
color range sets; and 
components used for independent testing and inspection.
Number of Samples: Submit two sets of Samples. Architect will retain one Sample set; remainder will be returned.  Retain one returned Sample set as a project record Sample.
Submit a single Sample where assembly details, workmanship, fabrication techniques, connections, operation, and other similar characteristics are to be demonstrated.
If variation in color, pattern, texture, or other characteristic is inherent in material or product represented by a Sample, submit at least three sets of paired units that show approximate limits of variations.
Product Schedule (when required or applicable): As required in individual Specification Sections, prepare a written summary indicating types of products required for the Work and their intended location. This may be submitted with the Product Data if all items on the schedule are included in the Product Data package. Include the following information in tabular form:
Type of product. Include unique identifier for each product indicated in the Contract Documents or assigned by Contractor if none is indicated.
Manufacturer and product name, and model number if applicable.
Number and name of room or space.
Location within room or space.
Qualification Data: Prepare and submit written information that demonstrates capabilities and experience of firm or person. Include lists of completed projects with project names and addresses, contact information of architects and University, and other information specified.
Design Data: Prepare and submit written and graphic information indicating compliance with indicated performance and design criteria in individual Specification Sections. Include list of assumptions and summary of loads. Include load diagrams if applicable. Provide name and version of software, if any, used for calculations. Number each page of submittal.
Certificates:
Edit for project. Identify specific certificates required for the project.
Certificates and Certifications Submittals: Submit a statement that includes signature of entity responsible for preparing certification. Certificates and certifications shall be signed by an officer or other individual authorized to sign documents on behalf of that entity. Provide a notarized signature where indicated.
Installer Certificates: Submit written statements on manufacturer's letterhead certifying that Installer complies with requirements in the Contract Documents and, where required, is authorized by manufacturer for this specific Project.
Manufacturer Certificates: Submit written statements on manufacturer's letterhead certifying that manufacturer complies with requirements in the Contract Documents. Include evidence of manufacturing experience where required.
Material Certificates: Submit written statements on manufacturer's letterhead certifying that material complies with requirements in the Contract Documents.
Product Certificates: Submit written statements on manufacturer's letterhead certifying that product complies with requirements in the Contract Documents.
Welding Certificates: Prepare written certification that welding procedures and personnel comply with requirements in the Contract Documents. Submit record of Welding Procedure Specification and Procedure Qualification Record on AWS forms. Include names of firms and personnel certified.
Test and Research Reports:
Edit for project. Identify specific reports required for the project and whether they are Action or Information submittals.
Compatibility Test Reports: Submit reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of compatibility tests performed before installation of product. Include written recommendations for primers and substrate preparation needed for adhesion.
Field Test Reports: Submit written reports indicating and interpreting results of field tests performed either during installation of product or after product is installed in its final location, for compliance with requirements in the Contract Documents.
Material Test Reports: Submit reports written by a qualified testing agency, on testing with requirements in the Contract Documents.
Preconstruction Test Reports: Submit reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of tests performed before installation of product, for compliance with performance requirements in the Contract Documents.
Product Test Reports: Submit written reports indicating that current product produced by manufacturer complies with requirements in the Contract Documents. Base reports on evaluation of tests performed by manufacturer and witnessed by a qualified testing agency, or on comprehensive tests performed by a qualified testing agency.
Research Reports: Submit written evidence, from a model code organization acceptable to authorities having jurisdiction, that product complies with building code in effect for Project. Include the following information:
Name of evaluation organization.
Date of evaluation.
Time period when report is in effect.
Product and manufacturers' names.
Description of product.
Test procedures and results.
Limitations of use.
Corrective Action Report: Testing agency shall submit written documentation of any defects found and any corrective action taken, or proposed solutions. 
Resubmission Summary:
   Provide summary of changes from previous submission.
   Include responses to review comments from previous submission.
DELETE SECTION BELOW IF IT DOES NOT APPLY
DELEGATED-DESIGN SERVICES
Performance and Design Criteria: Where professional design services or certifications by a design professional are specifically required of Contractor by the Contract Documents, provide products and systems complying with specific performance and design criteria indicated.
If criteria indicated are insufficient to perform services or certification required, submit a written request for additional information to Architect.
Delegated-Design Services Certification: In addition to Shop Drawings, Product Data, and other required submittals, submit digitally signed PDF file of certificate, signed and sealed by the responsible design professional, for each product and system specifically assigned to Contractor to be designed or certified by a design professional.
Indicate that products and systems comply with performance and design criteria in the Contract Documents. Include list of codes, loads, and other factors used in performing these services.
DELETE PARAGRAPH BELOW IF IT DOES NOT APPLY
BIM Incorporation: Incorporate delegated-design drawing and data files into BIM established for Project.
Prepare delegated-design drawings in the same digital data software program, version, and operating system as original Drawings
PRODUCTS (Not Used)
EXECUTION 
Provide bookmarks in submittal PDF as follows:
Submittal Bookmark Example: The following bookmark example is based on using an outline type arrangement with each line linked to the appropriate submittal page. Match Table of Contents:
UMB Submittal Identification Form
CM/Contractor Transmittal
CM/Contractor Replies (Resubmittal Only)
Consultant’s Comments
Manufacturer’s Transmittal
Manufacturer’s Replies (Resubmittal Only)
Product Data  
Product A (Example for A: 2.2 Shut Off Valves)
Product B (Example for B: 2.4 Check Valves)
Product C (Example for C: 2.5 Special Valves)
Fabrication Drawings
Drawing 1
Drawing 2
Drawing 3	
END OF SECTION
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