University of Maryland, Baltimore
Bressler Research Building – Seventh Floor Renovation	Project No: 10-357
95% Construction Document Submission Phase	March 11, 2011
SECTION 017839 - PROJECT RECORD DOCUMENTS
Initial Issue Date: 8/6/2026  
(A/E shall edit specifications and blue text in header to meet project requirements. This includes but is not limited to updating Equipment and/or Material Model Numbers indicated in the specifications and adding any additional specifications that may be required by the project. Remove text underlines and highlights) 
GENERAL
RELATED DOCUMENTS
Retain or delete this article in all Sections of Project Manual.
Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 01 Specification Sections, apply to this Section.
SUMMARY
Section includes administrative and procedural requirements for Project Record Documents, including the following:
As-Built Drawings.
As-Built specifications.
Record Product Data.
Miscellaneous record submittals.
Asset management information
CLOSEOUT SUBMITTALS
As-Built Drawings: Contractor shall submit redline set of As-Built Drawings as annotated PDF electronic files, reflecting actual conditions of the Work as constructed.
Maintain electronic record markups continuously during construction. Post changes as they occur; do not wait until end of Project.
Record information shall include changes made by Change Orders, Construction Change Directives, field modifications, concealed conditions, rerouting of utilities, and actual equipment locations.
As-Built Drawings shall be coordinated with construction photographs where applicable.
As-Built Drawings shall be submitted through the University’s PMIS.
As-Built Specifications: Contractor shall submit annotated PDF electronic files of Project Specifications, including Addenda and Contract Modifications.
Clearly indicate actual products installed, substitutions approved, and selections made.
Reference related Change Orders and As-Built Drawings where applicable.
AS-BUILT DRAWINGS
General: Maintain Project As-Built Drawings to document actual conditions of the Work as constructed.
Record information continuously during construction. Do not defer recording until closeout.
Record information shall be based on field observations, measurements, and verified conditions.
Record information prior to concealment of Work.
Content: As-Built Drawings shall include, but are not limited to, the following:
Dimensional changes to Drawings.
Revisions to details shown on Drawings.
Locations and depths of underground utilities.
Routing of piping, conduits, and ductwork.
Electrical circuitry revisions.
Actual equipment locations and identification.
Field conditions and details not shown on original Drawings.
Changes made by Change Orders or Construction Change Directives.
Information shown schematically in the Contract Documents.
Field records for variable and concealed conditions.
Format: Submit As-Built Drawings as annotated PDF electronic files.
Organize files to correspond to the original Contract Drawing sheet numbering.
AS-BUILT SPECIFICATIONS
Preparation: Maintain one electronic copy of As-Built Specifications, including Addenda and Contract Modifications, marked to indicate actual construction conditions.
Clearly identify products installed where different from those specified.
Indicate substitutions and product options approved.
Reference related Change Orders and As-Built Drawings where applicable.
Format: Submit As-Built Specifications as annotated PDF electronic files.
MAINTENANCE OF AS-BUILT DOCUMENTS DURING CONSTRUCTION
Maintain Project As-Built Documents in electronic format using the University’s electronic project management system or an approved electronic system that is accessible by the owner.
Maintain As-Built Documents in a complete, legible, and current condition throughout construction.
Provide access to Project As-Built Documents for the University and Architect during normal working hours through the electronic project management system.
PRODUCTS (Not Used)
EXECUTION (Not Used)
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