## RPPR Timeline
Preparing for the NIH Research Performance and Progress Report (RPPR)
SPA Recommended Timeline
| Planning Timeline | 60 days prior to due date | 45 days prior to due date | 2 weeks prior to due date | 3 days prior to due date or sooner | NIH Due date
| Action | Request subrecipient documentation | Hold Team Coordination/RPPR Kick Off Meeting | Finalize Budget and Technical Information | Route RPPR to SPA for review | SPA Grants submits RPPR to NIH
UMB Federal RPPR Webpage Link |  | Request subrecipient financial and technical reporting and any data results to meet the Foreign Subrecipient Data Rquirement. | Determine if the unobligated balance will be 25% or more. If yes, identify the estimated carryover. | Route RPPR between PI and departmental staff to finalize all technical and nontechnical responses in the RPPR, including ASSIST for the Human Subjects Form if applicable. | PI routes the Final RPPR to SPA for review 3 full business days prior to the NIH due date. | Once questions and revisions have been resolved.
|  | *Use the UMB SPA RPPR Subrecipient Progress Report Form as a tool if you like. This is not mandatory. | Confirm persons worked on the grant at least one calendar month, Key Person effort, and determine if there have been or will be any Key Personnel Changes. Update eRA Commons Profiles if needed. | Confirm the total estimated unobligated balance and if over 25%. | PI and department administrator make revisions and troubleshoots errors with SPA.
|  | Request Subrecipient Biosketches and Other Support for Subrecipient Key Personnel with changes to active support and/or MFTRP certification from Sub Key Personnel. | If NonSnap, Start prepring a budget and budget justification for the next year's budget. | If Non SNAP, complete budget entry. | Communication during this time is key between the PI, Department, and SPA Grants. Availability and responsiveness during regular working hours is crucial to ensure a compliant and timely submission.
|  | Request supporting documentation for foreign affiliations. | Technical writing for RPPR responses should begin. Human Subjects Form updates in ASSIST should begin. Update in Clinicaltrials.gov if clincial trial so updates will populate in ASSIST. | Collect all subrecipient data and documentation needed to finalize the report.
Assumptions
*PI works with a team in their department to prepare the RPPR. Team Members may include grants and contracts, program, and finance staff.